MILESTONE & ACTIVITY LIST

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| PROJECT  NAME | TEAM  WORKERS | PROJECT  START DATE | PROJECT  END DATE | TOTAL  WEEKS |
| **SmartFarmer - IoT Enabled Smart Farming Application** | **Agnes Santhiya L**  **Anusuya Rani K**  **Subha Shenbagam S**  **Ramya M** | **August 22, 2022** | **November 19,2022** | **13 Weeks** |
| PROJECT MILESTONES & ACTIVITIES | | | | |
| MILESTONES | ACTIVITIES | STATUS | EXPECTED DATE | ACTUAL  DATE |
| Preparation Space | Pre-requisites | Completed | 22 - 27 Aug ,2022 | Aug 25,2022 |
| Registration |
| Environment set-up |
| Ideation Phase | Literature Survey | Completed | 29 Aug - 3 Sep, 2022 | Sep 1,2022 |
| Empathy Map | Completed | 5 - 10 Sep, 2022 | Sep 7,2022 |
| Brainstroming | Completed | 12 - 17Sep,2022 | Sep 15,2022 |
| Project Design Phase - I | Proposed Solution Document | Completed | 19 - 24 Sep,2022 | Sep 21,2022 |
| Problem Solution Fit | Completed | 26 Sep - 1 Oct, 2022 | Sep 30,2022 |
| Solution Architecture |
| Project Design  Phase - II | Customer Journey | Completed | 3 - 8 Oct, 2022 | Oct 6,2022 |
| Functional Requirements | Completed | 10 - 15 Oct, 2022 | Oct 14,2022 |
| Data Flow Diagram |
| Technology Architecture |
| Projecct Planning Phase | Sprint Delivery Plan | Completed | 17 - 22 Oct, 2022 | Oct 20,2022 |
| Prepare Milestone & Activity List |
| Project Development Phase | Project Development Delivery of Sprit - I | Completed | 24 - 29 Oct, 2022 | Oct 28,2022 |
| Project Development Delivery of Sprit - II | In Progess | 31 Oct - 5 Nov, 2022 | - |
| Project Development  Delivery of Sprit - III | In Progess | 7 - 12 Nov, 2022 | - |
| Project Development Delivery of Sprit - IV | In Progess | 14 - 19 Nov, 2022 | - |